## Cover
AM335x EVM LCD A Board PCB Design Specification Cover Sheet
Ver | Comments | Author | Date
0.5 | initial PCB Design Specification from rev. 1.2A | Damon Domke | 2012-02-28

## SchematicChecklist
ARM MPU Schematic Checklist
Reserved
No. | Description |  | Done (blank = no, Y = yes, F = problem to resolve) | Checked by
1 | Schematic device symbol pin numbers are correct |  | Y | ddomke
2 | All ground symbol names are displayed and defined |  | Y | ddomke
3 | No orphaned ground nets |  | Y | ddomke
4 | All power symbol names are displayed and defined |  | Y | ddomke
5 | Schematic device symbols are not missing pins |  | Y | ddomke
6 | Schematic device symbols do not have extra pins |  | Y | ddomke
7 | Schematic device symbols have thermal power pad or isolated ground power pad pins |  | Y | ddomke
8 | There are no orphaned nets. |  | Y | ddomke
9 | There are no unintentional aliased nets. |  | Y | ddomke
10 | All bus nets connect off page to the correct places (where applicable). |  | Y | ddomke
11 | Each schematic page has the ARM MPU Title Block with proper information |  | Y | ddomke
12 | Each schematic page has proper version shown: x.yz (where x = major revision number, y = minor revision number (PCB change), z = minor revision alpha character (blue wire/component change with no PCB change) |  | Y | ddomke
13 | Symbol for blank PCB is included in the schematic |  | Y | ddomke
14 | Mechanical parts needed for PCB assembly are included as symbols |  | Y | ddomke
15 | Bill of Materials has been generated and all device information is shown. (ref des, value, description, manufacturer, mfr part number, vendor, TI internal part number, PCB Footprint) |  | Y | ddomke

## PCBLayoutChecklist
ARM MPU PCB Layout Checklist
Reserved
No. | Description |  | Done (blank = no, Y = yes, F = problem to resolve) | Checked by
1 | Is PCB stackup correct? |  | Y | ddomke
2 | Are all signal trace constraints met? |  | Y | ddomke
3 | Are controlled impedance constraints factored into the PCB stackup? |  | Y | ddomke
4 | Do applicable device footprints have proper thermal pads. |  | Y | ddomke
5 | Are the thermal pad vias correct? |  | Y | ddomke
6 | Are there adequate number of vias per layer change on power nets? |  | Y | ddomke
7 | Are placement constraints met? |  | Y | ddomke
8 | Are the text on PCB constraints met? |  | Y | ddomke
9 | Do trace neckdowns to device pins remain wide enough for each net? |  | Y | ddomke
10 | Is PCB blank board part number in copper on the bottom side of the board? |  | Y | ddomke
11 | Is assembled PCB part number in silk screen on top side of board? |  | Y | ddomke
12 | Are mounting holes in the correct positions and are they the proper diameter? |  | Y | ddomke
13 | Are board edge connectors placed at the correct overhang or flush? |  | Y | ddomke
14 | Do board edge connectors have enough room between other connectors so that the mate cable's jack will fit properly when all cables are connected to the board? |  | Y | ddomke
15 | Does final PCB layout match the final schematic? |  | Y | ddomke

## DiagnosticTestChecklist
ARM MPU Board Diagnostic Test Checklist
Reserved
No. | Description |  | Done (blank = no, Y = yes, F = problem to resolve) | Checked by | Comments
1 | Has the latest diagnostic test code been fully run on this board? (record the version used in the comments section)
2 | Have all the power and signal tests been performed and passed? (see separate sheet)
3 | Has the board assembly been checked for incorrectly mounted components?
4 | Has the board assembly been checked for soldering problems?
5 | Has quality sticker been attached to the board showing the revision of the diagnostic test code used and the revision of this PCBDesignSpecification used (for Power and Signal Tests) during the testing process?

## MechanicalPlacement
Mechanical Placement Diagram

## Placement Details
Component Placement Requirement Details
|  | Perc Done | 100%
Total Items | 9 | Items Done | 9
| No | Description | Done | Verified (Reviewer)
| 1 | Components to be mounted on the bottom side of the board with passive components on top or bottom side. See mechanical diagram for critical component approximate placement | done | ddomke
| 2 | The entire bottom side is low clearance as it must mate to the bottom side of the AM335x baseboard or Gen Purp Daughterboard. | done | ddomke
| 3 | Place the 3 LCD connectors that mate to the AM335x baseboard at the correct locations on the bottom side of the board. | done | ddomke
| 4 | Place the LCD panel connector J4 on the top side of the board to line up with the LCD flex cable | done | ddomke
| 5 | Place the Capacitive Touch Screen connector on the bottom side of the board to line up with the Capacitive Touch Screen flex cable | done | ddomke
| 6 | Place the Resistive Touch Screen connector on the bottom side of the board to line up with the Resistive Touch Screen flex cable | done | ddomke
| 7 | LCD panel is to be placed (with double sided tape) directly on the top side of the board so place no components under the LCD on the top side of the board with the exception of the LCD connector J4. | done | ddomke
| 8 | Place J9 along side J6 such that an 8pin connector with the same pitch as both J6 & J9 will connect to both J6 & J9. J9 should be south of J6. | done | ddomke
| 9 | Place J10 so that the Three Five Touchscreen panel attaches properly | done | ddomke

## Signal Trace Details
[5 empty] | Signal Trace Routing Requirements | Perc Done | 96.43%
Total Items | 28 |  |  |  |  | Num Done | 27
| No | Signals | Pins | Components | Description | Priority (1=highest 5=lowest) | Done (blank=no; Y= yes; F = fail) | Verified By: | COMMENTS
| 1 | DGND | vias |  | GND to be ground plane | 5 | Y | ddomke | Place many vias connecting the two ground planes
| 2 | V3_3D_SRC, V3_3D, V3_3A_TS |  |  | Route as power traces at least 30mil wide or split power plane. | 3 | Y | ddomke
| 3 | GND_TS |  |  | Route as a split ground plane on layer 5. Make a single point of connection no larger than 100mil wide to the standard DGND plane. | 1 | Y | ddomke
| 4 | Touch_Y[11..0] |  |  | Route each as trace with parasitic routing capacitance of less than 50pF. Route as short as possible. Keep parasitic series resistance of each line less than 100ohms. Route as a group using minimum track and gap geometries. Separate these signals from Touch_X signals using a double width ground trace. | 1 | Y | ddomke
| 5 | Touch_X16-Y13, TOUCH_X17_Y12, Touch_X[17..0] |  |  | Route each as trace with parasitic routing capacitance of less than 50pF. Route as short as possible. Keep parasitic series resistance of each line less than 100ohms. Route as a group using minimum track and gap geometries. Separate these signals from Touch_Y signals using a double width ground trace. | 1 | Y | ddomke
| 6 | V2_75D, V_VADD_TSC_2V75, VDD_1v8_TS |  |  | Route as power traces at least 30mil wide or split power plane. | 3 | Y | ddomke
| 7 | V1_8D |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 8 | VI2CD |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 9 | V5_0D |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke
| 10 | VEXP |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke | segment from C40 pad to pin 2 of U5 needs to be 30mil (neck down only where needed)
| 11 | LCD_PCLK/BCLK/CCLK, LCD_HSYNC/BHSYNC/CHSYNC, LCD_VSYNC/BVSYNC/CVSYNC, LCD_DEN/BDEN/CDEN, LCD_DATA[4..0]/BB[7..3]/CBB[7..3], LCD_DATA[10..5]/BG[7..2]/CBG[7..2], LCD_DATA[15..11]/BR[7..3]/CBR[7..3], LCD_DATA16/BB2/CBB2, LCD_DATA17/BR2/CBR2, LCD_DATA18/BB1/CBB1, LCD_DATA19/BG1/CBG1, LCD_DATA20/BR1/CBR1, LCD_DATA21/BB0/CBB0, LCD_DATA22/BG0/CBG0, LCD_DATA23/BR0/CBR0 |  | J1/J2 to U4 to RP1-RP4 to J4 | Keep lengths within 50mil of LCD_PCLK/BCLK/CCLK | 1 | Y | ddomke
| 12 | VGL_-7V, VGL, VGL_DRV |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke
| 13 | VGH_15V, VGH |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke
| 14 | AVDD_10V, AVDD10_IND, |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke
| 15 | VDD_LCD, VCOM |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke | VDD_LCD is too narrow;2 vias for VDD_LCD from U3
| 16 | VGHFB, VGLFB, VGL_REF |  |  | Route as power traces at least 15mil wide | 5 | Y | ddomke
| 17 | AVDD |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 18 | V1, V2, V3, V4, V5, V6, V7, V8, V9, V10 |  |  | Route as power traces at least 15mil wide or split power plane. | 4 | Y | ddomke
| 19 | LED+, LED- |  |  | Route as power traces at least 30mil wide or split power plane. | 3 | Y | ddomke | LED+ segment from C42 pad to U5 needs to be 30mil (neck down only where needed). Shave off some of the bevel of BKLT_SW trace so a wider trace of LED+ can be used.
| 20 | BKLT_L, BKLT_SW |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 21 | GNDA_TSC |  |  | Route as power traces at least 30mil wide or split power plane. | 5 | Y | ddomke
| 22 | VLCD_3_3D |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 23 | VLCD_2_75D |  |  | Route as power traces at least 30mil wide or split power plane. | 4 | Y | ddomke
| 24 | VLCD_2_75DFB, VLCD_3_3DFB |  |  | Route as power traces at least 15mil wide or split power plane. | 5 | Y | ddomke
| 25 | LCD_PCLK/BCLK/CCLK, LCD_HSYNC/BHSYNC/CHSYNC, LCD_VSYNC/BVSYNC/CVSYNC, LCD_DEN/BDEN/CDEN, LCD_DATA[4..0]/BB[7..3]/CBR[7..3], LCD_DATA[10..5]/BG[7..2]/CBG[7..2], LCD_DATA[15..11]/BR[7..3]/CBB[7..3], LCD_DATA16/BB2/CBR2, LCD_DATA17/BR2/CBB2, LCD_DATA18/BB1/CBR1, LCD_DATA19/BG1/CBG1, LCD_DATA20/BR1/CBB1, LCD_DATA21/BB0/CBR0, LCD_DATA22/BG0/CBG0, LCD_DATA23/BR0/CBB0 |  | J1/J2 to U4 to RP2,RP4, RP5, RP7 to J4 | Keep lengths within 50mil of LCD_PCLK/BCLK/CCLK | 1 | Y | ddomke
| 26 | TSC_AIN[3..0] |  | J6 to J3 | Route with at least 15mil traces | 5 | Y | ddomke
| 27 | TSC_AIN[3..0] |  | J9 to J3 | Route with at least 15mil traces | 5 | Y | ddomke
| 28 | TSC_AIN[3..0] |  | J10 to J3 | Route with at least 15mil traces | 5 |  | ddomke

## Net Length Check
Version: | 16.3
Comment: | Date/Time : October 04, 2011 01:07:23 PM
Comment: | ######################################################################
Comment: | Do not edit the following "States:" and "Columns:" lines.
Comment: | They are required for re-import into the spreadsheet.
Comment: | It is permitted to swap columns in this spreadsheet, as long as
Comment: | 1. the columns stay intact so that the State and Column pairs are the same, and
Comment: | 2. the column and state names themselves aren't changed.
Comment:
States: |  | ELECTRICAL_CONSTRAINT_SET | PROPAGATION_DELAY_PATH_TYPE | PIN_DELAY:2 | PIN_DELAY:3 | PROPAGATION_DELAY_MIN | PROPAGATION_DELAY_MIN_ACTUAL | PROPAGATION_DELAY_MIN_MARGIN | PROPAGATION_DELAY_MAX | PROPAGATION_DELAY_MAX_ACTUAL | PROPAGATION_DELAY_MAX_MARGIN
Comment: | Groupings: |  |  | Pin Delay |  | Prop Delay |  |  | Prop Delay
Columns: | Objects | Referenced Electrical CSet | Pin Pairs | Pin 1 | Pin 2 | Min | Actual | Margin | Max | Actual | Margin
Comment: | Units: |  |  | mil | mil | ns |  |  | ns
Comment: | ######################################################################
Design: | am335x_evm_lcdaboard_3H0005_layout_rev1_1a | [6 empty] | 0.017 MIL |  |  | 0.074 MIL
Bus: | BB | [6 empty] | 10.032 MIL |  |  | 1.73 MIL
Net: | BB0 | [6 empty] | 45.116 MIL |  |  | 14.884 MIL
Pin Pair: | U4.J5:RP3.1 |  |  |  |  | 100.000 MIL | 145.116 MIL | 45.116 MIL | 160.000 MIL | 145.116 MIL | 14.884 MIL
Pin Pair: | U4.J5:RP5.8 |  |  |  |  | 100.000 MIL | 145.116 MIL | 45.116 MIL | 160.000 MIL | 145.116 MIL | 14.884 MIL
Net: | BB1 | [6 empty] | 10.032 MIL |  |  | 49.968 MIL
Pin Pair: | U4.J6:RP3.2 |  |  |  |  | 100.000 MIL | 110.032 MIL | 10.032 MIL | 160.000 MIL | 110.032 MIL | 49.968 MIL
Pin Pair: | U4.J6:RP5.7 |  |  |  |  | 100.000 MIL | 110.032 MIL | 10.032 MIL | 160.000 MIL | 110.032 MIL | 49.968 MIL
Net: | BB2 | [6 empty] | 53.836 MIL |  |  | 6.164 MIL
Pin Pair: | U4.K5:RP3.3 |  |  |  |  | 100.000 MIL | 153.836 MIL | 53.836 MIL | 160.000 MIL | 153.836 MIL | 6.164 MIL
Pin Pair: | U4.K5:RP5.6 |  |  |  |  | 100.000 MIL | 153.836 MIL | 53.836 MIL | 160.000 MIL | 153.836 MIL | 6.164 MIL
Net: | BB3 | [6 empty] | 13.294 MIL |  |  | 46.706 MIL
Pin Pair: | U4.K6:RP3.4 |  |  |  |  | 100.000 MIL | 113.294 MIL | 13.294 MIL | 160.000 MIL | 113.294 MIL | 46.706 MIL
Pin Pair: | U4.K6:RP5.5 |  |  |  |  | 100.000 MIL | 113.294 MIL | 13.294 MIL | 160.000 MIL | 113.294 MIL | 46.706 MIL
Net: | BB4 | [6 empty] | 58.27 MIL |  |  | 1.73 MIL
Pin Pair: | U4.L5:RP3.5 |  |  |  |  | 100.000 MIL | 158.270 MIL | 58.27 MIL | 160.000 MIL | 158.270 MIL | 1.73 MIL
Pin Pair: | U4.L5:RP5.4 |  |  |  |  | 100.000 MIL | 158.270 MIL | 58.27 MIL | 160.000 MIL | 158.270 MIL | 1.73 MIL
Net: | BB5 | [6 empty] | 16.556 MIL |  |  | 43.444 MIL
Pin Pair: | U4.L6:RP3.6 |  |  |  |  | 100.000 MIL | 116.556 MIL | 16.556 MIL | 160.000 MIL | 116.556 MIL | 43.444 MIL
Pin Pair: | U4.L6:RP5.3 |  |  |  |  | 100.000 MIL | 116.556 MIL | 16.556 MIL | 160.000 MIL | 116.556 MIL | 43.444 MIL
Net: | BB6 | [6 empty] | 56.515 MIL |  |  | 3.485 MIL
Pin Pair: | U4.M5:RP3.7 |  |  |  |  | 100.000 MIL | 156.515 MIL | 56.515 MIL | 160.000 MIL | 156.515 MIL | 3.485 MIL
Pin Pair: | U4.M5:RP5.2 |  |  |  |  | 100.000 MIL | 156.515 MIL | 56.515 MIL | 160.000 MIL | 156.515 MIL | 3.485 MIL
Net: | BB7 | [6 empty] | 29.891 MIL |  |  | 30.109 MIL
Pin Pair: | U4.M6:RP3.8 |  |  |  |  | 100.000 MIL | 129.891 MIL | 29.891 MIL | 160.000 MIL | 129.891 MIL | 30.109 MIL
Pin Pair: | U4.M6:RP5.1 |  |  |  |  | 100.000 MIL | 129.891 MIL | 29.891 MIL | 160.000 MIL | 129.891 MIL | 30.109 MIL
Bus: | BG |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 7.516 MIL | 160.000 MIL |  | 3.24 MIL
Net: | BG0 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 56.76 MIL | 160.000 MIL |  | 3.24 MIL
Pin Pair: | U4.E5:RP2.1 |  |  |  |  | 100.000 MIL | 156.760 MIL | 56.76 MIL | 160.000 MIL | 156.760 MIL | 3.24 MIL
Net: | BG1 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 15.806 MIL | 160.000 MIL |  | 44.194 MIL
Pin Pair: | U4.E6:RP2.2 |  |  |  |  | 100.000 MIL | 115.806 MIL | 15.806 MIL | 160.000 MIL | 115.806 MIL | 44.194 MIL
Net: | BG2 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 52.194 MIL | 160.000 MIL |  | 7.806 MIL
Pin Pair: | U4.F5:RP2.3 |  |  |  |  | 100.000 MIL | 152.194 MIL | 52.194 MIL | 160.000 MIL | 152.194 MIL | 7.806 MIL
Net: | BG3 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 12.544 MIL | 160.000 MIL |  | 47.456 MIL
Pin Pair: | U4.F6:RP2.4 |  |  |  |  | 100.000 MIL | 112.544 MIL | 12.544 MIL | 160.000 MIL | 112.544 MIL | 47.456 MIL
Net: | BG4 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 48.932 MIL | 160.000 MIL |  | 11.068 MIL
Pin Pair: | U4.G5:RP2.5 |  |  |  |  | 100.000 MIL | 148.932 MIL | 48.932 MIL | 160.000 MIL | 148.932 MIL | 11.068 MIL
Net: | BG5 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 9.282 MIL | 160.000 MIL |  | 50.718 MIL
Pin Pair: | U4.G6:RP2.6 |  |  |  |  | 100.000 MIL | 109.282 MIL | 9.282 MIL | 160.000 MIL | 109.282 MIL | 50.718 MIL
Net: | BG6 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 45.671 MIL | 160.000 MIL |  | 14.329 MIL
Pin Pair: | U4.H5:RP2.7 |  |  |  |  | 100.000 MIL | 145.671 MIL | 45.671 MIL | 160.000 MIL | 145.671 MIL | 14.329 MIL
Net: | BG7 |  | All Drivers/All Receivers |  |  | 100.000 MIL |  | 7.516 MIL | 160.000 MIL |  | 52.484 MIL
Pin Pair: | U4.H6:RP2.8 |  |  |  |  | 100.000 MIL | 107.516 MIL | 7.516 MIL | 160.000 MIL | 107.516 MIL | 52.484 MIL
Bus: | BR | [6 empty] | 37.287 MIL |  |  | 0.074 MIL
Net: | BR0 | [6 empty] | 99.643 MIL |  |  | 0.357 MIL
Pin Pair: | U4.A5:RP1.1 |  |  |  |  | 100.000 MIL | 199.643 MIL | 99.643 MIL | 200.000 MIL | 199.643 MIL | 0.357 MIL
Pin Pair: | U4.A5:RP7.8 |  |  |  |  | 100.000 MIL | 199.643 MIL | 99.643 MIL | 200.000 MIL | 199.643 MIL | 0.357 MIL
Net: | BR1 | [6 empty] | 80.478 MIL |  |  | 19.522 MIL
Pin Pair: | U4.A6:RP1.2 |  |  |  |  | 100.000 MIL | 180.478 MIL | 80.478 MIL | 200.000 MIL | 180.478 MIL | 19.522 MIL
Pin Pair: | U4.A6:RP7.7 |  |  |  |  | 100.000 MIL | 180.478 MIL | 80.478 MIL | 200.000 MIL | 180.478 MIL | 19.522 MIL
Net: | BR2 | [6 empty] | 99.926 MIL |  |  | 0.074 MIL
Pin Pair: | U4.B5:RP1.3 |  |  |  |  | 100.000 MIL | 199.926 MIL | 99.926 MIL | 200.000 MIL | 199.926 MIL | 0.074 MIL
Pin Pair: | U4.B5:RP7.6 |  |  |  |  | 100.000 MIL | 199.926 MIL | 99.926 MIL | 200.000 MIL | 199.926 MIL | 0.074 MIL
Net: | BR3 | [6 empty] | 63.693 MIL |  |  | 36.307 MIL
Pin Pair: | U4.B6:RP1.4 |  |  |  |  | 100.000 MIL | 163.693 MIL | 63.693 MIL | 200.000 MIL | 163.693 MIL | 36.307 MIL
Pin Pair: | U4.B6:RP7.5 |  |  |  |  | 100.000 MIL | 163.693 MIL | 63.693 MIL | 200.000 MIL | 163.693 MIL | 36.307 MIL
Net: | BR4 | [6 empty] | 94.495 MIL |  |  | 5.505 MIL
Pin Pair: | U4.C5:RP1.5 |  |  |  |  | 100.000 MIL | 194.495 MIL | 94.495 MIL | 200.000 MIL | 194.495 MIL | 5.505 MIL
Pin Pair: | U4.C5:RP7.4 |  |  |  |  | 100.000 MIL | 194.495 MIL | 94.495 MIL | 200.000 MIL | 194.495 MIL | 5.505 MIL
Net: | BR5 | [6 empty] | 44.273 MIL |  |  | 55.727 MIL
Pin Pair: | U4.C6:RP1.6 |  |  |  |  | 100.000 MIL | 144.273 MIL | 44.273 MIL | 200.000 MIL | 144.273 MIL | 55.727 MIL
Pin Pair: | U4.C6:RP7.3 |  |  |  |  | 100.000 MIL | 144.273 MIL | 44.273 MIL | 200.000 MIL | 144.273 MIL | 55.727 MIL
Net: | BR6 | [6 empty] | 74.429 MIL |  |  | 25.571 MIL
Pin Pair: | U4.D5:RP1.7 |  |  |  |  | 100.000 MIL | 174.429 MIL | 74.429 MIL | 200.000 MIL | 174.429 MIL | 25.571 MIL
Pin Pair: | U4.D5:RP7.2 |  |  |  |  | 100.000 MIL | 174.429 MIL | 74.429 MIL | 200.000 MIL | 174.429 MIL | 25.571 MIL
Net: | BR7 | [6 empty] | 37.287 MIL |  |  | 62.713 MIL
Pin Pair: | U4.D6:RP1.8 |  |  |  |  | 100.000 MIL | 137.287 MIL | 37.287 MIL | 200.000 MIL | 137.287 MIL | 62.713 MIL
Pin Pair: | U4.D6:RP7.1 |  |  |  |  | 100.000 MIL | 137.287 MIL | 37.287 MIL | 200.000 MIL | 137.287 MIL | 62.713 MIL
Bus: | B_CNTRL |  | All Drivers/All Receivers |  |  | 185.000 MIL |  | 0.464 MIL | 190.000 MIL |  | 0.173 MIL
Net: | BCLK |  | All Drivers/All Receivers |  |  | 185.000 MIL |  | 2.163 MIL | 190.000 MIL |  | 2.837 MIL
Pin Pair: | U4.N6:RP4.2 |  |  |  |  | 185.000 MIL | 187.163 MIL | 2.163 MIL | 190.000 MIL | 187.163 MIL | 2.837 MIL
Net: | BDEN |  | All Drivers/All Receivers |  |  | 185.000 MIL |  | 2.294 MIL | 190.000 MIL |  | 2.706 MIL
Pin Pair: | U4.R6:RP4.6 |  |  |  |  | 185.000 MIL | 187.294 MIL | 2.294 MIL | 190.000 MIL | 187.294 MIL | 2.706 MIL
Net: | BHSYNC |  | All Drivers/All Receivers |  |  | 185.000 MIL |  | 0.464 MIL | 190.000 MIL |  | 4.536 MIL
Pin Pair: | U4.P6:RP4.4 |  |  |  |  | 185.000 MIL | 185.464 MIL | 0.464 MIL | 190.000 MIL | 185.464 MIL | 4.536 MIL
Net: | BVSYNC |  | All Drivers/All Receivers |  |  | 185.000 MIL |  | 4.827 MIL | 190.000 MIL |  | 0.173 MIL
Pin Pair: | U4.R5:RP4.5 |  |  |  |  | 185.000 MIL | 189.827 MIL | 4.827 MIL | 190.000 MIL | 189.827 MIL | 0.173 MIL
Bus: | CBB | [6 empty] | 0.633 MIL |  |  | 0.105 MIL
Net: | CBB0 | [6 empty] | 2.152 MIL |  |  | 0.639 MIL
Pin Pair: | J4.20:RP3.16 |  |  |  |  | 630.000 MIL | 634.361 MIL | 4.361 MIL | 635.000 MIL | 634.361 MIL | 0.639 MIL
Pin Pair: | J4.20:RP7.9 |  |  |  |  | 630.000 MIL | 632.152 MIL | 2.152 MIL | 635.000 MIL | 632.152 MIL | 2.848 MIL
Net: | CBB1 | [6 empty] | 2.676 MIL |  |  | 0.105 MIL
Pin Pair: | J4.21:RP3.15 |  |  |  |  | 660.000 MIL | 664.895 MIL | 4.895 MIL | 665.000 MIL | 664.895 MIL | 0.105 MIL
Pin Pair: | J4.21:RP7.10 |  |  |  |  | 660.000 MIL | 662.676 MIL | 2.676 MIL | 665.000 MIL | 662.676 MIL | 2.324 MIL
Net: | CBB2 | [6 empty] | 3.159 MIL |  |  | 0.493 MIL
Pin Pair: | J4.22:RP3.14 |  |  |  |  | 630.000 MIL | 633.159 MIL | 3.159 MIL | 635.000 MIL | 633.159 MIL | 1.841 MIL
Pin Pair: | J4.22:RP7.11 |  |  |  |  | 630.000 MIL | 634.507 MIL | 4.507 MIL | 635.000 MIL | 634.507 MIL | 0.493 MIL
Net: | CBB3 | [6 empty] | 0.953 MIL |  |  | 4.027 MIL
Pin Pair: | J4.23:RP3.13 |  |  |  |  | 660.000 MIL | 660.953 MIL | 0.953 MIL | 665.000 MIL | 660.953 MIL | 4.047 MIL
Pin Pair: | J4.23:RP7.12 |  |  |  |  | 660.000 MIL | 660.973 MIL | 0.973 MIL | 665.000 MIL | 660.973 MIL | 4.027 MIL
Net: | CBB4 | [6 empty] | 3.194 MIL |  |  | 0.639 MIL
Pin Pair: | J4.24:RP3.12 |  |  |  |  | 630.000 MIL | 633.194 MIL | 3.194 MIL | 635.000 MIL | 633.194 MIL | 1.806 MIL
Pin Pair: | J4.24:RP7.13 |  |  |  |  | 630.000 MIL | 634.361 MIL | 4.361 MIL | 635.000 MIL | 634.361 MIL | 0.639 MIL
Net: | CBB5 | [6 empty] | 1.511 MIL |  |  | 1.201 MIL
Pin Pair: | J4.25:RP3.11 |  |  |  |  | 660.000 MIL | 661.511 MIL | 1.511 MIL | 665.000 MIL | 661.511 MIL | 3.489 MIL
Pin Pair: | J4.25:RP7.14 |  |  |  |  | 660.000 MIL | 663.799 MIL | 3.799 MIL | 665.000 MIL | 663.799 MIL | 1.201 MIL
Net: | CBB6 | [6 empty] | 2.099 MIL |  |  | 0.777 MIL
Pin Pair: | J4.26:RP3.10 |  |  |  |  | 630.000 MIL | 632.099 MIL | 2.099 MIL | 635.000 MIL | 632.099 MIL | 2.901 MIL
Pin Pair: | J4.26:RP7.15 |  |  |  |  | 630.000 MIL | 634.223 MIL | 4.223 MIL | 635.000 MIL | 634.223 MIL | 0.777 MIL
Net: | CBB7 | [6 empty] | 0.633 MIL |  |  | 2.5 MIL
Pin Pair: | J4.27:RP3.9 |  |  |  |  | 640.000 MIL | 640.633 MIL | 0.633 MIL | 645.000 MIL | 640.633 MIL | 4.367 MIL
Pin Pair: | J4.27:RP7.16 |  |  |  |  | 640.000 MIL | 642.500 MIL | 2.5 MIL | 645.000 MIL | 642.500 MIL | 2.5 MIL
Bus: | CBG |  | All Drivers/All Receivers |  |  | 635.000 MIL |  | 0.017 MIL | 640.000 MIL |  | 1.381 MIL
Net: | CBG0 |  | All Drivers/All Receivers |  |  | 635.000 MIL |  | 3.036 MIL | 640.000 MIL |  | 1.964 MIL
Pin Pair: | J4.12:RP2.16 |  |  |  |  | 635.000 MIL | 638.036 MIL | 3.036 MIL | 640.000 MIL | 638.036 MIL | 1.964 MIL
Net: | CBG1 |  | All Drivers/All Receivers |  |  | 665.000 MIL |  | 0.017 MIL | 670.000 MIL |  | 4.983 MIL
Pin Pair: | J4.13:RP2.15 |  |  |  |  | 665.000 MIL | 665.017 MIL | 0.017 MIL | 670.000 MIL | 665.017 MIL | 4.983 MIL
Net: | CBG2 |  | All Drivers/All Receivers |  |  | 635.000 MIL |  | 0.937 MIL | 640.000 MIL |  | 4.063 MIL
Pin Pair: | J4.14:RP2.14 |  |  |  |  | 635.000 MIL | 635.937 MIL | 0.937 MIL | 640.000 MIL | 635.937 MIL | 4.063 MIL
Net: | CBG3 |  | All Drivers/All Receivers |  |  | 665.000 MIL |  | 2.45 MIL | 670.000 MIL |  | 2.55 MIL
Pin Pair: | J4.15:RP2.13 |  |  |  |  | 665.000 MIL | 667.450 MIL | 2.45 MIL | 670.000 MIL | 667.450 MIL | 2.55 MIL
Net: | CBG4 |  | All Drivers/All Receivers |  |  | 635.000 MIL |  | 3.53 MIL | 640.000 MIL |  | 1.47 MIL
Pin Pair: | J4.16:RP2.12 |  |  |  |  | 635.000 MIL | 638.530 MIL | 3.53 MIL | 640.000 MIL | 638.530 MIL | 1.47 MIL
Net: | CBG5 |  | All Drivers/All Receivers |  |  | 665.000 MIL |  | 3.198 MIL | 670.000 MIL |  | 1.802 MIL
Pin Pair: | J4.17:RP2.11 |  |  |  |  | 665.000 MIL | 668.198 MIL | 3.198 MIL | 670.000 MIL | 668.198 MIL | 1.802 MIL
Net: | CBG6 |  | All Drivers/All Receivers |  |  | 635.000 MIL |  | 3.619 MIL | 640.000 MIL |  | 1.381 MIL
Pin Pair: | J4.18:RP2.10 |  |  |  |  | 635.000 MIL | 638.619 MIL | 3.619 MIL | 640.000 MIL | 638.619 MIL | 1.381 MIL
Net: | CBG7 |  | All Drivers/All Receivers |  |  | 675.000 MIL |  | 3.49 MIL | 680.000 MIL |  | 1.51 MIL
Pin Pair: | J4.19:RP2.9 |  |  |  |  | 675.000 MIL | 678.490 MIL | 3.49 MIL | 680.000 MIL | 678.490 MIL | 1.51 MIL
Bus: | CBR | [6 empty] | 0.119 MIL |  |  | 0.648 MIL
Net: | CBR0 | [6 empty] | 0.78 MIL |  |  | 2.608 MIL
Pin Pair: | J4.4:RP1.16 |  |  |  |  | 590.000 MIL | 592.392 MIL | 2.392 MIL | 595.000 MIL | 592.392 MIL | 2.608 MIL
Pin Pair: | J4.4:RP5.9 |  |  |  |  | 590.000 MIL | 590.780 MIL | 0.78 MIL | 595.000 MIL | 590.780 MIL | 4.22 MIL
Net: | CBR1 | [6 empty] | 0.158 MIL |  |  | 1.112 MIL
Pin Pair: | J4.5:RP1.15 |  |  |  |  | 590.000 MIL | 590.158 MIL | 0.158 MIL | 595.000 MIL | 590.158 MIL | 4.842 MIL
Pin Pair: | J4.5:RP5.10 |  |  |  |  | 590.000 MIL | 593.888 MIL | 3.888 MIL | 595.000 MIL | 593.888 MIL | 1.112 MIL
Net: | CBR2 | [6 empty] | 13.365 MIL
Pin Pair: | J4.6:RP1.14 |  |  |  |  | 590.000 MIL | 603.365 MIL | 13.365 MIL
Pin Pair: | J4.6:RP5.11 |  |  |  |  | 590.000 MIL | 674.521 MIL | 84.521 MIL
Net: | CBR3 | [6 empty] | 0.119 MIL |  |  | 0.648 MIL
Pin Pair: | J4.7:RP1.13 |  |  |  |  | 610.000 MIL | 614.352 MIL | 4.352 MIL | 615.000 MIL | 614.352 MIL | 0.648 MIL
Pin Pair: | J4.7:RP5.12 |  |  |  |  | 610.000 MIL | 610.119 MIL | 0.119 MIL | 615.000 MIL | 610.119 MIL | 4.881 MIL
Net: | CBR4 | [6 empty] | 3.51 MIL |  |  | 0.652 MIL
Pin Pair: | J4.8:RP1.12 |  |  |  |  | 590.000 MIL | 593.510 MIL | 3.51 MIL | 595.000 MIL | 593.510 MIL | 1.49 MIL
Pin Pair: | J4.8:RP5.13 |  |  |  |  | 590.000 MIL | 594.348 MIL | 4.348 MIL | 595.000 MIL | 594.348 MIL | 0.652 MIL
Net: | CBR5 | [6 empty] | 2.439 MIL |  |  | 1.041 MIL
Pin Pair: | J4.9:RP1.11 |  |  |  |  | 630.000 MIL | 633.959 MIL | 3.959 MIL | 635.000 MIL | 633.959 MIL | 1.041 MIL
Pin Pair: | J4.9:RP5.14 |  |  |  |  | 630.000 MIL | 632.439 MIL | 2.439 MIL | 635.000 MIL | 632.439 MIL | 2.561 MIL
Net: | CBR6 | [6 empty] | 0.222 MIL |  |  | 0.758 MIL
Pin Pair: | J4.10:RP1.10 |  |  |  |  | 600.000 MIL | 604.242 MIL | 4.242 MIL | 605.000 MIL | 604.242 MIL | 0.758 MIL
Pin Pair: | J4.10:RP5.15 |  |  |  |  | 600.000 MIL | 600.222 MIL | 0.222 MIL | 605.000 MIL | 600.222 MIL | 4.778 MIL
Net: | CBR7 | [6 empty] | 0.643 MIL |  |  | 3.815 MIL
Pin Pair: | J4.11:RP1.9 |  |  |  |  | 640.000 MIL | 641.185 MIL | 1.185 MIL | 645.000 MIL | 641.185 MIL | 3.815 MIL
Pin Pair: | J4.11:RP5.16 |  |  |  |  | 640.000 MIL | 640.643 MIL | 0.643 MIL | 645.000 MIL | 640.643 MIL | 4.357 MIL
Bus: | C_CNTRL |  | All Drivers/All Receivers |  |  | 585.000 MIL |  | 5.166 MIL | 605.000 MIL |  | 1.852 MIL
Net: | CCLK |  | All Drivers/All Receivers |  |  | 585.000 MIL |  | 5.166 MIL | 605.000 MIL |  | 14.834 MIL
Pin Pair: | J4.28:RP4.15 |  |  |  |  | 585.000 MIL | 590.166 MIL | 5.166 MIL | 605.000 MIL | 590.166 MIL | 14.834 MIL
Net: | CDEN |  | All Drivers/All Receivers |  |  | 585.000 MIL |  | 12.401 MIL | 605.000 MIL |  | 7.599 MIL
Pin Pair: | J4.29:RP4.11 |  |  |  |  | 585.000 MIL | 597.401 MIL | 12.401 MIL | 605.000 MIL | 597.401 MIL | 7.599 MIL
Net: | CHSYNC |  | All Drivers/All Receivers |  |  | 585.000 MIL |  | 18.148 MIL | 605.000 MIL |  | 1.852 MIL
Pin Pair: | J4.30:RP4.13 |  |  |  |  | 585.000 MIL | 603.148 MIL | 18.148 MIL | 605.000 MIL | 603.148 MIL | 1.852 MIL
Net: | CVSYNC |  | All Drivers/All Receivers |  |  | 585.000 MIL |  | 8.236 MIL | 605.000 MIL |  | 11.764 MIL
Pin Pair: | J4.31:RP4.12 |  |  |  |  | 585.000 MIL | 593.236 MIL | 8.236 MIL | 605.000 MIL | 593.236 MIL | 11.764 MIL
Bus: | LCD_CNTRL |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 5.808 MIL | 1710.000 MIL |  | 0.25 MIL
Net: | LCD_DEN |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 9.25 MIL | 1710.000 MIL |  | 0.75 MIL
Pin Pair: | U4.R1:J2.17 |  |  |  |  | 1700.000 MIL | 1709.250 MIL | 9.25 MIL | 1710.000 MIL | 1709.250 MIL | 0.75 MIL
Net: | LCD_HSYNC |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 9.75 MIL | 1710.000 MIL |  | 0.25 MIL
Pin Pair: | U4.P1:J2.18 |  |  |  |  | 1700.000 MIL | 1709.750 MIL | 9.75 MIL | 1710.000 MIL | 1709.750 MIL | 0.25 MIL
Net: | LCD_PCLK |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 7.756 MIL | 1710.000 MIL |  | 2.244 MIL
Pin Pair: | J2.16:U4.N1 |  |  |  |  | 1700.000 MIL | 1707.756 MIL | 7.756 MIL | 1710.000 MIL | 1707.756 MIL | 2.244 MIL
Net: | LCD_VSYNC |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 5.808 MIL | 1710.000 MIL |  | 4.192 MIL
Pin Pair: | U4.R2:J1.17 |  |  |  |  | 1700.000 MIL | 1705.808 MIL | 5.808 MIL | 1710.000 MIL | 1705.808 MIL | 4.192 MIL
Bus: | LCD_DATA |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.047 MIL | 1710.000 MIL |  | 0.251 MIL
Net: | LCD_DATA0 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 6.339 MIL | 1710.000 MIL |  | 3.661 MIL
Pin Pair: | J1.4:U4.K1 |  |  |  |  | 1700.000 MIL | 1706.339 MIL | 6.339 MIL | 1710.000 MIL | 1706.339 MIL | 3.661 MIL
Net: | LCD_DATA1 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 6.419 MIL | 1710.000 MIL |  | 3.581 MIL
Pin Pair: | J1.3:U4.L2 |  |  |  |  | 1700.000 MIL | 1706.419 MIL | 6.419 MIL | 1710.000 MIL | 1706.419 MIL | 3.581 MIL
Net: | LCD_DATA2 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 2.333 MIL | 1710.000 MIL |  | 7.667 MIL
Pin Pair: | J1.6:U4.L1 |  |  |  |  | 1700.000 MIL | 1702.333 MIL | 2.333 MIL | 1710.000 MIL | 1702.333 MIL | 7.667 MIL
Net: | LCD_DATA3 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 2.785 MIL | 1710.000 MIL |  | 7.215 MIL
Pin Pair: | J1.5:U4.M2 |  |  |  |  | 1700.000 MIL | 1702.785 MIL | 2.785 MIL | 1710.000 MIL | 1702.785 MIL | 7.215 MIL
Net: | LCD_DATA4 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 6.227 MIL | 1710.000 MIL |  | 3.773 MIL
Pin Pair: | J1.8:U4.M1 |  |  |  |  | 1700.000 MIL | 1706.227 MIL | 6.227 MIL | 1710.000 MIL | 1706.227 MIL | 3.773 MIL
Net: | LCD_DATA5 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.047 MIL | 1710.000 MIL |  | 9.953 MIL
Pin Pair: | J1.7:U4.F2 |  |  |  |  | 1700.000 MIL | 1700.047 MIL | 0.047 MIL | 1710.000 MIL | 1700.047 MIL | 9.953 MIL
Net: | LCD_DATA6 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 9.749 MIL | 1710.000 MIL |  | 0.251 MIL
Pin Pair: | U4.F1:J2.15 |  |  |  |  | 1700.000 MIL | 1709.749 MIL | 9.749 MIL | 1710.000 MIL | 1709.749 MIL | 0.251 MIL
Net: | LCD_DATA7 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 3.9 MIL | 1710.000 MIL |  | 6.1 MIL
Pin Pair: | U4.G2:J2.9 |  |  |  |  | 1700.000 MIL | 1703.900 MIL | 3.9 MIL | 1710.000 MIL | 1703.900 MIL | 6.1 MIL
Net: | LCD_DATA8 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 3.475 MIL | 1710.000 MIL |  | 6.525 MIL
Pin Pair: | U4.G1:J2.11 |  |  |  |  | 1700.000 MIL | 1703.475 MIL | 3.475 MIL | 1710.000 MIL | 1703.475 MIL | 6.525 MIL
Net: | LCD_DATA9 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 1.301 MIL | 1710.000 MIL |  | 8.699 MIL
Pin Pair: | U4.H2:J2.13 |  |  |  |  | 1700.000 MIL | 1701.301 MIL | 1.301 MIL | 1710.000 MIL | 1701.301 MIL | 8.699 MIL
Net: | LCD_DATA10 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 5.775 MIL | 1710.000 MIL |  | 4.225 MIL
Pin Pair: | J1.10:U4.H1 |  |  |  |  | 1700.000 MIL | 1705.775 MIL | 5.775 MIL | 1710.000 MIL | 1705.775 MIL | 4.225 MIL
Net: | LCD_DATA11 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.517 MIL | 1710.000 MIL |  | 9.483 MIL
Pin Pair: | J1.16:U4.B1 |  |  |  |  | 1700.000 MIL | 1700.517 MIL | 0.517 MIL | 1710.000 MIL | 1700.517 MIL | 9.483 MIL
Net: | LCD_DATA12 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.9 MIL | 1710.000 MIL |  | 9.1 MIL
Pin Pair: | U4.C2:J1.9 |  |  |  |  | 1700.000 MIL | 1700.900 MIL | 0.9 MIL | 1710.000 MIL | 1700.900 MIL | 9.1 MIL
Net: | LCD_DATA13 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 9.557 MIL | 1710.000 MIL |  | 0.443 MIL
Pin Pair: | J2.10:U4.C1 |  |  |  |  | 1700.000 MIL | 1709.557 MIL | 9.557 MIL | 1710.000 MIL | 1709.557 MIL | 0.443 MIL
Net: | LCD_DATA14 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.217 MIL | 1710.000 MIL |  | 9.783 MIL
Pin Pair: | U4.D2:J1.12 |  |  |  |  | 1700.000 MIL | 1700.217 MIL | 0.217 MIL | 1710.000 MIL | 1700.217 MIL | 9.783 MIL
Net: | LCD_DATA15 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 4.141 MIL | 1710.000 MIL |  | 5.859 MIL
Pin Pair: | U4.D1:J2.7 |  |  |  |  | 1700.000 MIL | 1704.141 MIL | 4.141 MIL | 1710.000 MIL | 1704.141 MIL | 5.859 MIL
Net: | LCD_DATA16 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 6.225 MIL | 1710.000 MIL |  | 3.775 MIL
Pin Pair: | J2.8:U4.K2 |  |  |  |  | 1700.000 MIL | 1706.225 MIL | 6.225 MIL | 1710.000 MIL | 1706.225 MIL | 3.775 MIL
Net: | LCD_DATA17 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 4.277 MIL | 1710.000 MIL |  | 5.723 MIL
Pin Pair: | U4.B2:J2.5 |  |  |  |  | 1700.000 MIL | 1704.277 MIL | 4.277 MIL | 1710.000 MIL | 1704.277 MIL | 5.723 MIL
Net: | LCD_DATA18 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 3.216 MIL | 1710.000 MIL |  | 1.784 MIL
Pin Pair: | U4.J1:J2.6 |  |  |  |  | 1785.000 MIL | 1788.216 MIL | 3.216 MIL | 1790.000 MIL | 1788.216 MIL | 1.784 MIL
Net: | LCD_DATA19 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 0.195 MIL | 1710.000 MIL |  | 9.805 MIL
Pin Pair: | J1.13:U4.E1 |  |  |  |  | 1700.000 MIL | 1700.195 MIL | 0.195 MIL | 1710.000 MIL | 1700.195 MIL | 9.805 MIL
Net: | LCD_DATA20 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 2.024 MIL | 1710.000 MIL |  | 2.976 MIL
Pin Pair: | U4.A1:J2.3 |  |  |  |  | 1635.000 MIL | 1637.024 MIL | 2.024 MIL | 1640.000 MIL | 1637.024 MIL | 2.976 MIL
Net: | LCD_DATA21 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 7.52 MIL | 1710.000 MIL |  | 2.48 MIL
Pin Pair: | U4.J2:J2.4 |  |  |  |  | 1700.000 MIL | 1707.520 MIL | 7.52 MIL | 1710.000 MIL | 1707.520 MIL | 2.48 MIL
Net: | LCD_DATA22 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 8.61 MIL | 1710.000 MIL |  | 1.39 MIL
Pin Pair: | U4.E2:J1.14 |  |  |  |  | 1700.000 MIL | 1708.610 MIL | 8.61 MIL | 1710.000 MIL | 1708.610 MIL | 1.39 MIL
Net: | LCD_DATA23 |  | All Drivers/All Receivers |  |  | 1700.000 MIL |  | 4.844 MIL | 1710.000 MIL |  | 5.156 MIL
Pin Pair: | U4.A2:J1.11 |  |  |  |  | 1700.000 MIL | 1704.844 MIL | 4.844 MIL | 1710.000 MIL | 1704.844 MIL | 5.156 MIL
Bus: | POWER_TRACE
Net: | VCOMC+
Net: | VCOMC-
Net: | VCOMIN
Net: | VGHFB
Net: | VLCD_2_75DEN
Net: | VLCD_2_75DFB
Net: | VLCD_3_3DEN
Net: | V3_3D
Bus: | 30MIL
Net: | AVDD10_IND
Net: | BKLT_L
Net: | BKLT_SW
Net: | LED+
Net: | LED-
Net: | VGL_DRV
Net: | VLCD_2_75D
Net: | VLCD_3_3D
Net: | V2_75D
Net: | AM335X_I2C0_SCL
Net: | AM335X_I2C0_SDA
Net: | AM335X_TSC_CLK
Net: | AM335X_TSC_GIO0
Net: | AM335X_TSC_GIO1
Net: | AM335X_TSC_RSV0
Net: | AM335X_TSC_RSV1_VREF
Net: | AVDD
Net: | AVDD10_FB
Net: | BKLT_EN
Net: | CAPTSC_INTN
Net: | CAPTSC_RESETN
Net: | COMP
Net: | COMP_CAP
Net: | DGND
Net: | DITH
Net: | GNDA_TSC
Net: | GND_TS
Net: | IDMEM_WP
Net: | LCDA_PIN18
Net: | LCD_AVDD_EN
Net: | LCD_BACKLIGHTEN
Net: | LCD_ENBKL
Net: | MODE3
Net: | N674108
Net: | N758197
Net: | N758244
Net: | N802446
Net: | N885528
Net: | N16829785
Net: | N16936909
Net: | N16967100
Net: | N16975010
Net: | N16975030
Net: | N16975032
Net: | N17020718
Net: | PWRLED_R
Net: | PWR_EN
Net: | RSTB
Net: | SHLR
Net: | STBYB
Net: | SYS_RESETN
Net: | TCH_ADDR
Net: | TCH_E4
Net: | TCH_G3
Net: | TOUCH_I2CSCL
Net: | TOUCH_I2CSDA
Net: | TOUCH_MOSI
Net: | TOUCH_SCK
Net: | TOUCH_X0
Net: | TOUCH_X1
Net: | TOUCH_X2
Net: | TOUCH_X3
Net: | TOUCH_X4
Net: | TOUCH_X5
Net: | TOUCH_X6
Net: | TOUCH_X7
Net: | TOUCH_X8
Net: | TOUCH_X9
Net: | TOUCH_X10
Net: | TOUCH_X11
Net: | TOUCH_X12
Net: | TOUCH_X13
Net: | TOUCH_X14
Net: | TOUCH_X15
Net: | TOUCH_X16
Net: | TOUCH_X16-Y13
Net: | TOUCH_X17
Net: | TOUCH_X17_Y12
Net: | TOUCH_Y0
Net: | TOUCH_Y1
Net: | TOUCH_Y2
Net: | TOUCH_Y3
Net: | TOUCH_Y4
Net: | TOUCH_Y5
Net: | TOUCH_Y6
Net: | TOUCH_Y7
Net: | TOUCH_Y8
Net: | TOUCH_Y9
Net: | TOUCH_Y10
Net: | TOUCH_Y11
Net: | TSC_AIN0
Net: | TSC_AIN1
Net: | TSC_AIN2
Net: | TSC_AIN3
Net: | TSC_AIN4
Net: | TSC_AIN5
Net: | TSC_AIN6
Net: | TSC_AIN7
Net: | TSC_I2CSCL
Net: | TSC_I2CSDA
Net: | UPDN
Net: | VCOM
Net: | VDDLCD_BASE
Net: | VDD_LCD
Net: | VEXPD
Net: | VGH
Net: | VGL
Net: | VGL_FB
Net: | VGL_REF
Net: | VI2CD
Net: | VLCDBUF_B
Net: | VLCD_3_3DFB
Net: | V_VADD_TSC_2V75
Net: | V1
Net: | V1_8D
Net: | V2
Net: | V3
Net: | V3_3A_TS
Net: | V3_3D_SRC
Net: | V4
Net: | V5
Net: | V5_0D
Net: | V6
Net: | V7
Net: | V8
Net: | V9
Net: | V10
Net: | XM_SEL

## Mechanical Details
Mechanical Requirements
No | Description | Done (blank = no; Y = yes) | Verified By:
1 | Place mounting holes as per the mini_ITX specification. Note that the bottom of this LCD A board mates to the bottom of the AM335x base board. This board also mates to the bottom of the GP Daughterboard so a second set of partial mini-ITX holes must be placed in the appropriate positions. | Y | ddomke
2 | The PCB should be FR4 material with 6 layer stackup with the following assignments: 1=signal 2=split power plane 3=signal 4=signal 5=ground plane 6=signal | Y | ddomke
3 | PCB should be 1.588mm (62.5mil) thick. | Y | ddomke
4 | PCB should be mini-ITX width (170mm) and 110mm high. | Y | ddomke
5 | Place a note in the fabrication drawing that all vias are to have soldermask. | Y | ddomke
6 | no via in pad; | Y | ddomke

## TextonPCB
Silkscreen Text Requirements
No | Description | Done (blank = no; Y = yes) | Verified By: | Comments
1 | Place Texas Instruments logo on the top side lower left corner | Y | ddomke
2 | Place the text "ARM MPU" on the bottom side | Y | ddomke
3 | Place the text "AM335x EVM LCD A Board" on the top side on the south edge | Y | ddomke
4 | Place the text "PN#: 3H0005" in copper on the bottom side | Y | ddomke
5 | Place the text "GND" next to TP3 | Y | ddomke
6 | Place the text "Assm PN#: 4P0015" on the bottom side | Y | ddomke
7 | Place the text "POWER" next to D3 | Y | ddomke
8 | Place the text "SN#: __________" on the top side along the south edge. | Y | ddomke
9 | Place the text "Rev. 1.3A" on the top side on the south-southeast edge |  | ddomke
10 | Place pin 1 orientation text by all components that are not non-polarized capacitors or dual pad resistors | Y | ddomke

## Assembly Requirements
Default Assembly Settings Requirements
No | Description | Done (blank = no; Y = yes) | Verified By:
1 | Install all parts except the list of DNI parts in BOM | Y | ddomke
2 | After assembly, U5 is to be programmed with supplied data file. Then R71 must be installed. | Y | ddomke

## PowerandSignalTests
Power and Signal Tests
|  | Perc Done | 100%
Total Items | 1 | Items Done | 1
| No | Description | Done | Verified (Reviewer)
| 1 | N/A | done

## ChangesfromRev1.0A
Changes from Rev. 1.0A Board
| No. | Description | Schematic Changes | PCB Layout Changes | Done | Verified By: | comments
| 1 | · UPDN signal needs pulldown instead of pullup | Y | Y | done | ddomke
| 2 | · J5 pcb decal has wrong pin numbers (swapped in schematic) |  | Y | done | ddomke | need to move U5 and components so LED+ & LED- are not changing layers
| 3 | · LCD connector J4 is shifted by 1 pin | Y | Y | done | ddomke
| 4 | · Pullups are needed on the I2C lines after the translator | Y | Y | done | ddomke
| 5 | · Resistive touch 4x1 connector seems to have 2 & 3 pins swapped but the schematic is correct. (check in layout) |  | Y | done | ddomke
| 6 | · U11 & U12 pin 4 should be not connected | Y | Y | done | ddomke
| 7 | · Add resistors to allow the swap of the R & B data lines after the transceiver | Y | Y | done | ddomke
| 8 | DNI C48-C51 | Y |  | done | ddomke
| 9 | Update TPS61081 schematic symbol with pin for Thermal PAD and connect to ground | Y | Y | done | ddomke
| 10 | · Add a pulldown on the DITH signal | Y | Y | done | ddomke
| 11 | · Bring AIN[7..4] to a similar connector as touch screen connector | Y | Y | done | ddomke

## ChangesfromRev1.1A
Changes from Rev. 1.1A Board
| No. | Description | Schematic Changes | PCB Layout Changes | Done | Verified By: | comments
| 1 | Add a connector for the Three Five resistive connector | Y | Y | done | ddomke

## ChangesfromRev1.2A
Changes from Rev. 1.2A Board
| No. | Description | Schematic Changes | PCB Layout Changes | Done | Verified By: | comments
| 1 | Change backlight driver to constant current mode with proper current limit setting | Y | Y |  | ddomke