## Checklist 1.0
Design Change List
Product: |  | CC85XX Headset
Revision: |  | 1.3
ID | Date |  | Initials | Done | Comments by designer | Done by | Reviewed
1 | 2010-07-22 | R29 and R28 changed to 0402 0R | OAT | X | Remove filter on output due to low volume | OAT
2 | 2010-07-22 | R15 Changed value to 330K | OAT | X | Regulated voltage changed to achieve lower power consumption | OAT
3 | 2010-07-22 | C17 and C19 removed | OAT | X | Remove filter on output due to low volume | OAT
4 | 2010-07-22 | Button B1 schematic symbol and connection changed | OAT | X | Corrected originial fault | OAT
5 | 2010-07-22 | U10,U11,C18,R24,C16,C10,C32,C33,C20,C31,C13,R31,R22,R26,R30 Removed | OAT | X | No LDO's needed to get good performance | OAT
6 | 2010-08-03 | Changed polarity for D2 (LED) | OAT | X | When powering off board the led would stay on | OAT
7 | 2010-10-14 | Changed value of R23 to R_0402 | OAT | X | Causing R23 to be mounted when not mounted | OAT
8 | 2010-11-30 | Changed version to correct x.x format new rev v1.3 | OAT | X |  | OAT
9 | 2010-11-30 | Corrected CC2505 into CC8531 | OAT | X | CC2505 does not exist | OAT
10 | 2010-11-30 | Updates to purchase list to follow standard conventions | OAT | X |  | OAT
11 | 2010-11-30 | Changed drill size of the two holes on B1 to ease mounting | OAT | X |  | OAT
12 | 2010-11-30 | Moved B1 0.5mm left(outward) to ease mounting | OAT | X |  | OAT
13
14
15
16
17
18